## Status Definitions
Definitions of Status
Status | Definition
On Schedule | The deliverable was not completed during this FY but is on schedule to be complete by the FY that it is due (as indicated by blue cells in the table).
Behind Schedule | The deliverable was not complete during this FY and is behind schedule to be completed by the FY that it is due (as indicated by blue cells in the table).
Completed for FY | The deliverable was completed during the FY but will be due again in future FYs.
Complete | The deliverable was completed during the FY and is completed for the Plan as a whole (not due in future FY)
No Work Scheduled | The deliverable was not completed during this FY because no work was scheduled to be completed during this FY.

## Partnership
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective P-1 Existing and new NPS Management Program partnerships result in an increased understanding of NPS issues and the importance of clean water. | Milestone P-1.1 Existing and new NPS partners and stakeholders participate in statewide NPS programs and watershed projects. Partners: NHDES, Section 319 grantees, Section 604(b) grantees, watershed organizations, municipalities, nongovernmental organizations and universities | Measure P-1.1a NHDES staff present NPS related issues in two NPS outreach activities per year through planning assistance or presentations. | [5 empty] | Tom Swenson |  | Behind Schedule | Hosted a Lake Phosphorus Control Plan Workshop on March 20. Due to my temporary reassignment to the Beach Program because of staffing shortages during the summer months, two public presentation opportunities had to be turned down.
|  | Measure P-1.1b NPS Management Program staff assist with two watershed project outreach-related activities annually. | [5 empty] | Tom Swenson |  | Behind Schedule | Behind on assisting with watershed project outreach. I will work with and engage stake holders in 2026.
| Milestone P-1.2 NPS Management Program partner/stakeholder audiences, including 319 grantees, have access to NPS information and are able to obtain answers to NPS-related questions. Partners: NHDES NPS Management Program, Section 319 grantees, Section 604(b) grantees, municipalities and watershed organizations | Measure P-1.2a Press releases are distributed for Section 319 Grant projects when awarded. | [5 empty] | Andrea Bejtlich |  | Complete | The press release was posted on the NHDES website on 09/03/2025
|  | Measure P-1.2b Regular updates are provided using the Watershed Protection and Restoration Forum. | [5 empty] | Katie Zink |  | Complete | Updates added as they come in.
| Milestone P-1.3* New Hampshire municipalities are familiar with low-impact | Measure P-1.3a At least 20 New Hampshire Stormwater Coalition meetings are coordinated and facilitated annually. | [5 empty] | Tom Swenson |  | Complete | 22 New Hampshire Stormwater Coalition meetings were coordinated and facilitated.
| development practices, local stormwater regulations, technical assistance and other technical and financial resources. Partners: NHDES, Natural Resource Outreach Coalition, municipalities, Lower Merrimack Valley Stormwater Coalition and Seacoast Stormwater Coalition | Measure P-1.3b Outreach materials are reviewed or updated annually for New Hampshire MS4 permittees to meet water quality goals. | [5 empty] | Tom Swenson |  |  | All outreach materials were reviewed and updated as needed during 2025. Over the year, outreach materials were presented at the two New Hampshire Stormwater coalitions to help permittees meet the NH MS4 Permit requirements.
|  | Measure P-1.3c Coordinate with New Hampshire MS4 stormwater coalition chairs to convene a regional stormwater coalition meeting. | [5 empty] | Deb Loiselle | Tom Swenson | On Schedule
|  | Measure P-1.3d NPS Management Program staff maintain the New Hampshire MS4 website with meetings, resources and calendar updates. | [5 empty] | Deb Loiselle | Tom Swenson | Complete | Information and resources are added on a regular basis and done in a timely fashion.
|  | Measure P-1.3e NPS Management Program staff update New Hampshire stormwater coalitions with the most current impairments and TMDLs from the Section 303(d) and 305(b) assessments. | [5 empty] | Tom Swenson |  | On Schedule
| Milestone P-1.4 Align priority watersheds with the TMDL Program. Partners: NHDES NPS Management Program and NHDES TMDL Program | Measure P-1.4a TMDL Program staff consult the NPS Management Program watershed priority list to identify priority watersheds for TMDL development. | [5 empty] | Steve Landry | Matt Wood and Ken Edwardson | On Schedule | Collaboration with the TMDL Coordinator diminished in 2025 due to reassignment and his departure from NHDES. Will work with NHDES Water Quality Section staff on this Measure in following years.
|  | Measure P-1.4b Watersheds with TMDLs are priorities for watershed-based plan development. | [5 empty] | Katie Zink |  | Complete | This is taken into account during selection.
| Milestone P-1.5 The CWSRF Program regularly funds stormwater and nonpoint source projects, including development of watershed-based plans. Partners: NHDES NPS Management Program and NHDES CWSRF Program | Measure P-1.5 At least six eligible CWSRF loans available for stormwater planning and nonpoint source projects are on the project priority list to be funded annually. | [5 empty] | Deb Loiselle |  | Complete | The final 2025 CWSRF PPL has authorized 7 Planning Only projects and 2 Combo projects that have a planning component.

## PriotityWatersheds
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective PW-1 Grant Funding is awarded to projects with the greatest likelihood for successful restoration or protection activities. | Milestone PW-1.1 Annual grant solicitation process utilizes watershed prioritization as the basis for funding projects. Partner: NHDES NPS Management Program. | Measure PW-1.1 100% of grants awarded annually are in watersheds deemed a priority by NPS Management Program staff. | Yes | Yes | Yes | Yes | Yes | Katie Zink |  | Completed for FY | This is taken into account during selection.
Objective PW-2 Watershed-based plans are developed and implemented in priority watersheds. | Milestone PW-2.1 Restoration and protection projects identified in existing watershed-based plans are implemented. Partners: NHDES NPS Management Program and Section 319 grantees. | Measure PW-2.1 Sixteen restoration and four protection projects are completed through a competitive grant award process by 2029. | No data | No data | No data | No data | Yes | Katie Zink |  | On Schedule
| Milestone PW-2.2 New watershed-based plans are developed, and existing watershed-based plans are updated, where needed, to comply with EPA’s nine minimum elements (a) through (i). Partners: NHDES Watershed Assistance Section, Section 319 and 604(b) grantees and CWSRF partners. | Measure PW-2.2 Five new or updated watershed-based plans or alternative watershed-based plans in restoration or protection priority watersheds that meet EPA’s nine minimum elements (a) through (i) are developed by 2029. | No data | No data | No data | No data | Yes | Katie Zink |  | On Schedule
| Milestone PW-2.3 Progress toward implementing watershed-based plans is efficiently tracked, including action item implementation, condition and maintenance surveying of SCMs and other relevant information. Partners: NHDES NPS Management Program and Section 319 grantees. | Measure PW-2.3a Five SCM condition assessments are completed per year to determine general conditions of 319 or CWSRF loan-funded SCM installations. | Yes | Yes | Yes | Yes | Yes | Andrea Bejtlich |  | Completed for FY | SCM site inspections conducted 9/16/2025, 9/18/2025, 9/23/2025 and 9/25/2025.
|  | Measure PW-2.3b Every SCM implementation project requires SCM Operation and Maintenance agreements to support follow-up maintenance for 319 or CWSRF loan funded SCMs to improve performance and life expectancy. | Yes | Yes | Yes | Yes | Yes | Andrea Bejtlich |  | Completed for FY | All Grant Agreements include the requirement for Operation and Maintenance agreements for SCMs implemented
Objective PW-3 Progress toward water quality improvement is quantified. | Milestone PW 3.1 Watershed-based plan implementation efforts result in measurable water quality benefits. Partners: NHDES NPS Management Program, Section 319 grantees and other monitoring programs. | Measure PW-3.1 Estimated annual reductions of nitrogen, phosphorus, sediment and other project-relevant parameters are reported annually into GRTS and included in the NPS Management Program Annual Report. | Yes | Yes | Yes | Yes | Yes | Andrea Bejtlich |  | Completed for FY | All annual load reductions are added into GRTS upon receipt. A total of 121.38 lbs per year of nitrogen, 39.36 lbs/ yr of phosphorus, and 666.13 tons of sediment were reduced by four projects and 11 stormwater control measures in FFY 25.
| Milestone PW-3.2 Potential assessment unit delisting, partial delisting and implementation projects are tracked so that EPA NPS Success Stories can be drafted as soon as possible. Partners: NHDES, Section 319 grantees, EPA and volunteer monitoring groups. | Measure PW-3.2 Confirmation monitoring is completed annually in watersheds where watershed-based plans have been implemented to determine whether delisting of water quality impairments is warranted. | Yes | Yes | Yes | Yes | Yes | Steve Landry | Amy Smagula, Bob Craycraft, and lake associations | Completed for FY | Closely tracking Nippo and Partridge Lake confirmation monitoring in 2025 forward to measure alum treatment effectivness relative to meeting Primary Contact Designated Use.
| Milestone PW-3.3 EPA NPS Success Stories (Types 1-5) are approved and published on EPA and NHDES websites to demonstrate program success. Partners: NHDES NPS Management Program, Section 319 grantees and EPA. | Measure PW-3.3 Two EPA-approved NPS Success Stories are completed by 2029. | No data | Yes | No data | No data | Yes | Katie Zink |  | On Schedule
| Milestone PW-3.4 NHDES and agency partners provide assistance to applicants seeking permits for in-lake treatments to prevent chronic cyanobacteria blooms and remove related impairments by addressing internal loading of phosphorus to lakes and ponds from benthic sediments. In-lake treatments occur once installations of SCMs to control external nutrient loading have achieved sufficient progress toward meeting pollutant load reduction targets established in watershed-based plans. Partners: NHDES, Section 319 grantees and Cyanobacteria Mitigation Fund grantees. | Measure PW – 3.4 Successful treatment of one lake or pond using a permitted in-lake treatment to inactivate internal loading of phosphorus from benthic sediment when warranted under Administrative Rule Env-Wq 2300. | No data | No data | No data | No data | Yes | Sally Soule | Amy Smagula | On Schedule | In-lake treatment was applied to Partridge Lake in summer 2025. Work continues to identify additional lakes for treatment.

## Program
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective 319-1 The NPS Management Program Plan is up-to-date and used to track satisfactory progress. | Milestone 319-1.1 Completion of annual milestones, objectives and goals in the NPS Management Program Plan are tracked and reported in the NPS Program Annual Report. Partner: NHDES NPS Management Program. | Measure 319-1.1 Documentation of completed plan elements in the NPS Annual Report, the Measures Tracking and Reporting System (MTRS) and other relevant reports and systems. | [5 empty] | Katie Zink |  | Completed for FY
| Milestone 319-1.2 The NPS Management Program Plan is updated every five years to reflect program changes and success toward meeting NPS Program goals and progress is reported annually. Partners: NHDES, existing NPS partners, and future NPS stakeholders to be determined. | Measure 319-1.2a The completed NPS Management Program Plan update for years 2030-2034 is approved by EPA prior to October 1, 2029. | [5 empty] | Steve Landry | NPS Staff | On Schedule | NPS Mgt Program Plan 2025 Results by Goal tracking spreadsheet developed and issued to WAS Leads for reporting by end of October 2025.
|  | Measure 319-1.2b The NPS Management Program Report is submitted to EPA annually. | [5 empty] | Katie Zink |  | Completed for FY
| Milestone 319-1.3 Grant work plans are developed, applications for Section 319 funding are submitted and required reports are completed. Partners: NHDES Watershed Assistance Section, EPA, 319 Grantees and NPS partners to be determined. | Measure 319-1.3a NPS Management Program staff work plans are recorded in the MTRS database with regular progress reporting. | [5 empty] | Katie Zink |  | Behind Schedule | Not completed by 9/30/2025. Staff is working to complete this.
|  | Measure 319-1.3b Annual grant progress reports are submitted to EPA. | [5 empty] | Katie Zink |  | Completed for FY
Objective 319-2 Funding is adequate to fulfill NPS Management Program Plan objectives and dollars are used efficiently and are consistent with legal obligations. | Milestone 319-2.1 Apply and manage Section 319 funding from EPA as part of the NHDES Performance Partnership Grant (PPG) and continuing environmental program grant. Partners: NHDES NPS Management Program and EPA. | Measure 319-2.1 Grant dollars are spent by the grant end date and no later than five years from the start date. | [5 empty] | Katie Zink |  | On Schedule | FFY21 grant was extended therefore ran for slightly more than 5 years, but the projects were not active for all of that time.
| Milestone 319-2.2 Update/review scoring criteria and project eligibility requirements for 319 and other funded projects managed by the NPS Management Program. Partner: NHDES Watershed Assistance Section. | Measure 319-2.2 Grant application scoring and eligibility criteria are reviewed and updated annually. | [5 empty] | Andrea Bejtlich |  | Completed for FY | The Watershed Assistance Grants information packet and pre-proposal application were reviewed during FFY 25.
| Milestone 319-2.3 Requests for Proposal (RFPs) for 319 sub-awards are released to allow ample time for state and EPA approval and the execution of 319 sub-awards by NHDES as soon as feasible after federal 319 dollars are made available. Partners: NHDES Watershed Assistance Section and EPA. | Measure 319-2.3 319 sub-awards are obligated within one year after the EPA grant award. | [5 empty] | Andrea Bejtlich |  | Completed for FY | FFY25 funds were made available in October 2025. Grant Agreements between NHDES and grantees receiving sub-awards were drafted and sent to grantees to review in October 2025. Projects are expected to begin work by January 2026.

## Developed Lands
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective DL-1 NPS Management Program partners understand the costs associated with managing stormwater from developed lands. | Milestone DL-1.1 Federal, state and local decision makers understand New Hampshire’s stormwater capital needs and associated costs and identify potential funding sources. Partners: NHDES, municipalities and New Hampshire stormwater coalitions. | Measure DL-1.1 Potential funding sources are identified as they become available, and announcements are provided to municipalities regarding viable sources. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | Announcements via email distribution lists (WAS & CWSRF), posting on the NHDES NH MS4 website, annual presentations through the Water Infrastructure Funding Workshop, word of mouth, and individual/entity contact with NHDES personnel.
| Milestone DL-1.2 The CWSRF is used for the development of an Asset Management Program for municipalities. Partners: NHDES, municipalities and New Hampshire stormwater coalitions. | Measure DL-1.2 At least four CWSRF Asset Management loans/ grants are awarded annually to New Hampshire municipalities specific to stormwater assets. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | The 2025 final CWSRF PPL awarded 5 Stormwater Asset Management Program grants specific to stormwater. There were a total of 7 (5 SW & 2 WW) grants awarded for Asset Management Programs.
Objective DL-2 NPS Management Program partners have access to an array of funding opportunities to implement stormwater-related projects. | Milestone DL-2.1 The 604(b) Water Quality Planning Grants are used for NPS and stormwater-related planning projects. Partners: NHDES Watershed Assistance Section and 604(b) Grantees. | Measure DL-2.1 At least one 604(b) grant is awarded to NPS and stormwater-related planning projects each year. | Yes | Yes | Yes | Yes | Yes | Katie Zink |  | Completed for FY
| Milestone DL-2.2 Municipalities pursue the development of individual or regional stormwater utilities in New Hampshire to provide adequate, diverse and sustainable funding of equitable stormwater programs. Partners: NHDES, legislators, municipalities, New Hampshire stormwater coalitions, NHCP and UNHSC. | Measure DL-2.2 Assistance is provided to municipalities to complete at least one new stormwater utility feasibility study by 2029. | No data | No data | No data | No data | Yes | Deb Loiselle |  | On Schedule
| Milestone DL-2.3 The CWSRF is used to fund NPS and stormwater projects in New Hampshire. Partners: NHDES CWSRF Program, municipalities and New Hampshire stormwater coalitions. | Measure DL-2.3a At least one annual meeting is held with the NHDES Wastewater Engineering Bureau todiscuss barriers to obtain CWSRF funds and work creatively to increase opportunities for stormwater and nonpoint source projects. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | Deb Loiselle meets reguarly with CWSRF personnel in the Design and Planning Section to discuss status updates, strategies, and barriers. Conservatively, meetings occur at least once per month. Deb Loiselle also participates in the OneWater initiative developed out of the Detign Thinking Workshop (DTW), is co-leading (with Katie Curtis in DWGWB) the Education and Outreach initiatives developed out of the DTW, team member of the Asset Management Program initiatives.
|  | Measure DL-2.3b* An annual announcement is made to New Hampshire Stormwater Coalitions and other New Hampshire municipalities to promote stormwater projects for CWSRF applications. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | Deb Loiselle announced the 2025 CWSRF solicitation at the following monthly meetings for both the NHLMV and SSC: March, April, and May. In addition, Deb Loiselle and Sarah Ridyard (WWEB) presented on the Asset Management Program grant at the April NHLMV and SSC meetings.
|  | Measure DL-2.3c CWSRF loans are awarded for priority NPS and stormwater, stormwater asset management, stormwater planning and stormwater resiliency planning CWSRF projects annually. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | The 2025 final CWSRF PPL awarded the following: 5 Stormwater Asset Management Programs, 7 Stormwater Planning only projects, 4 Stormwater Infrastructure only projects, and 2 Infrastructure with Planning Component projects. All awards are loans with the expection of the Stormwater Asset Management projects which are grants. The total amount awarded under the 2025 CWSRF PPL was $5,112,000. The stormwater category is inclusive of NPS.
| Milestone DL-2.4 NHDES Watershed Assistance Grants are used for nonpoint source and stormwater projects that protect or restore water quality in New Hampshire. Partners: NHDES, municipalities, regional planning commissions, nonprofit organizations, county conservation districts, state agencies, watershed associations, water suppliers and local advisory committees. | Measure DL-2.4 At least three priority NPS and stormwater projects that protect or restore water quality are awarded Watershed Assistance Grants annually. | Yes | Yes | Yes | Yes | Yes | Katie Zink |  | Completed for FY
Objective DL-3 State and local regulatory programs are more fully protective of water quality and minimize the stormwater impacts from developed lands. | Milestone DL-3.1 Determine whether changes are needed to the AoT Rules (Env-Wq 1500) to improve water quality protection and climate resilience. Partners: NHDES, NHDES AoT Bureau, New Hampshire Chapter of American Council of Engineering Companies and UNHSC. | Measure DL-3.1 The NHDES AoT section and NPS Management Program coordinate biannually to discuss potential changes to rules and regulations as they pertain to NPS pollution. | No data | Yes | No data | Yes | No data | Deb Loiselle |  | On Schedule
| Milestone DL-3.2 Attend CWSRF and Drinking Water State Revolving Fund (DWSRF) Sustainability Meetings. Partners: NHDES NPS Management Program, CWSRF Program and DWSRF Program. | Measure DL-3.2 At least six CWSRF and DWSRF Sustainability Meetings are attended annually. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle |  | Completed for FY | Deb Loiselle attended 7 meetings during the reporting period. She was unable to attend the remaining 5 during the months of May thru September due to staffing shortages and additional work she was doing as a result of a temporary reassignment of an individual she supervises.
Objective DL-4 Professional engineers, state and local regulators and regulated entities have an improved understanding of how stormwater SCMs function and perform over the long term. | Milestone DL-4.1* The use of methods as described in Appendix F of the 2017 New Hampshire Small MS4 General Permit to calculate phosphorus and nitrogen load reduction credits for structural and non-structural SCMs are encouraged. Partners: NHDES NPS Management Program, NHDES AoT Bureau, CWSRF Program, ARM Program, UNHSC, municipalities and watershed groups | Measure DL-4.1 The load reductions resulting from SCM implementation activities are credited using methods outlined in the 2017 New Hampshire Small MS4 General Permit. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle | Tom Swenson & Sally Soule | Completed for FY | 27 NH MS4 permittees used PTAP to report load reductions resulting from SCM implementation activities and in accordance with the 2017 NH MS4 General Permit.
| Milestone DL-4.2* The tracking and accounting of NPS implementation activities through the Great Bay Pollution Tracking and Accounting Project (PTAP) is promoted. The use and adoption of PTAP by municipalities beyond the Great Bay watershed is encouraged. Partners: NHDES NPS Management Program, UNHSC and municipalities. | Measure DL-4.2 The PTAP database is utilized by municipalities to track implementation of SCMs and quantification of SCMs and the performance of other NPS implementation activities. | Yes | Yes | Yes | Yes | Yes | Sally Soule |  | Completed for FY | PTAP is used by communities in the Great Bay watershed and the Lower Merrimack Valley region for NPS tracking and reporting. UNH produced annual reports for 2025 for PTAP users.
| Milestone DL-4.3 The use of watershed pollution hot spot maps in planning and implementing cost effective NPS controls are promoted and encouraged. The use of hot spot mapping methods for other regions of the state is encouraged. Partners: NHDES NPS Management Program, UNHSC, NH GRANIT, regional planning commissions, municipalities and watershed groups. | Measure DL-4.3 Pollution hot spot maps are produced and/or updated; regional and municipal partners use maps to plan and implement NPS management actions annually. | Yes | Yes | Yes | Yes | Yes | Sally Soule |  | Completed for FY | Communities continue to use hot spot maps to identify and prioritize NPS implementation activities. Discussions continue with UNH regarding ways to improve hot spot mapping.
| Milestone DL-4.4 The New Hampshire Stormwater Manual is reviewed bi-annually. Partners: UNHSC and NHDES. | Measure DL-4.4 The Stormwater Manual is reviewed by NPS Management Program and UNHSC staff. New technology and scientific data are reviewed, and the manual is revised as appropriate. | No data | No data | Yes | No data | No data | Deb Loiselle |  | On Schedule
| Milestone DL-4.5 Outreach is conducted for the updated New Hampshire Stormwater Manual. Partners: UNHSC and NHDES. | Measure DL-4.5 Outreach on the updated stormwater manual is conducted. | Yes | Yes | No data | No data | No data | Deb Loiselle |  | Complete | There have been 4 informational sessions completed during this reporting period and were hosted by the following entities: NHDES (3/5/2025 virtual), Lake Winnipesaukee Watershed Alliance (5/29/2025 in-person), Annual Drinking Water Source Protection Conference (6/12/25 in-person), and Environmental Business Council (9/3/25 virtual). Presentations are done in collaboration with NHDES WAS & AoT, UNHSC, and CEI.
| Milestone DL-4.6 Southeast Watershed Alliance Post Construction Stormwater Management Standards are finalized. Partners: UNHSC and NHDES. | Measure DL-4.6 Southeast Watershed Alliance Post Construction Stormwater Management Standards are finalized by 2029. | No data | No data | No data | No data | Yes | Deb Loiselle |  | On Schedule
Objective DL-5 Stormwater SCMs are adequately maintained and continue to function through their intended design life. | Milestone DL-5.1 Hands-on training and technical assistance is provided to municipal public works staff and professional landscapers on the installation and maintenance of low-impact development stormwater practices. Partners: New Hampshire Municipal Association members, UNHSC, New Hampshire Landscape Association, UNH Cooperative Extension, New Hampshire Sea Grant and NHDES NPS Management Program. | Measure DL-5.1 One training is conducted biannually. | No data | Yes | No data | Yes | No data | Tom Swenson |  | On Schedule
Objective DL-6 New Hampshire residents understand the connection between land use and water quality. | Milestone DL-6.1 Resources are provided to local organizations interested in participating in the SOAKNH Program. Partners: NHDES | Measure DL-6.1 SOAKNH Program resources are updated and made available annually. | Yes | Yes | Yes | Yes | Yes | Rob Livingston
| Milestone DL-6.2 Collaborations with stakeholder organizations are established to build capacity to create local SOAKNH groups who work in their communities to spread the “Soak Up the Rain” message and install SCMs. Partners: NHDES and SOAKNH Program-eligible organizations. | Measure DL-6.2 At least one local watershed group is engaged annually. | Yes | Yes | Yes | Yes | Yes | Rob Livingston
| Milestone DL-6.3 Site-level SCMs are installed through the SOAKNH program. Partners: NHDES and SOAKNH Program-eligible organizations. | Measure DL-6.3 At least one SCM installation is completed annually. Installation information including location and pollutant loading estimates are reported on the SOAKNH website. | Yes | Yes | Yes | Yes | Yes | Rob Livingston

## Hydro and Habitat
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective H-1 NPS Management Program maintains partnerships and capacity to implement living shoreline projects throughout New Hampshire to address hydrologic and habitat modification. | Milestone H-1.1 Living shoreline projects are identified throughout New Hampshire. Potential living shoreline projects are identified by NPS Management Program partners for partial funding through NPS Management Program grants. Partners: NHDES Coastal Program, NHFG, NOAA Office for Coastal Management, UNH Coastal Habitats Restoration Team, watershed organizations, lake associations, municipalities and conservation districts. | Measure H-1.1 A list of living shoreline projects and their partners that would be eligible for partial NPS funding is developed. | Yes | Yes | Yes | No data | No data | Sally Soule |  | No Work Scheduled
| Milestone H-1.2 Implement living shoreline project(s). A proposal for NPS funding to implement at least one living shoreline project with project partners is submitted for partial funding and the project is implemented. Partners: NHDES Coastal Program, NHDES Land Resources Management, NHFG, UNH Coastal Habitat Restoration Team, watershed organizations, lake associations, municipalities and conservation districts. | Measure H-1.2a A living shoreline proposal for partial NPS funding is developed and submitted. | No data | No data | Yes | No data | No data | Sally Soule | Tracy Degnan, RCCD | On Schedule | Rockingham Country Conservation District (RCCD) submitted an FY25 319 proposal for living shoreline implementation on the Exeter River in Exeter, NH. The proposal was selected to receive funding.
|  | Measure H-1.2b If the full proposal is selected for partial NPS funding, the project is implemented and a final report of living shoreline project implementation is on file and available as reference for future NPS living shoreline project partners. | No data | No data | No data | Yes | Yes | Sally Soule | Tracy Degnan, RCCD | On Schedule | The proposal above was selected for 319 funding and design work is underway for the living shoreline.
Objective H-2 Stream crossings that do not meet geomorphic integrity thresholds, AOP criteria or their appropriate recurrence interval are identified within watershed-based plans. | Milestone H-2.1 Freshwater stream crossings and tidal crossings not meeting geomorphic, AOP or the recurrence interval threshold appropriate for the drainage area associated with the identified crossings are identified and prioritized for restoration efforts within watershed-based plans or geomorphic assessments performed at the watershed scale. Partners: NHDES Coastal Program, Great Bay Stewards, NHDES Geological Survey, watershed organizations, municipalities, NHDOT, The Nature Conservancy and NHFG. | Measure H-2.1 By 2029, the NHDES Stream Crossing Initiative Assessment Protocols are fully executed in at least two watersheds undergoing the development of a watershed-based plan, geomorphic assessment, feasibility study or flood risk study. Protocol results are then used to develop a priority ranking for culverts, barriers and stream crossings in need of removal or upgrade to improve geomorphic equilibrium, resilience, AOP, hydraulic and hydrologic connectivity and full tidal cycling. | No data | No data | No data | No data | Yes | Sally Soule |  | No Work Scheduled
Objective H-3 Barrier and dam removals in New Hampshire result in NPS Success Stories. | Milestone H-3.1 Freshwater and tidal dams or barriers that co-occur with AUs on the 303(d) List for NPS-related parameters; or fail to meet geomorphic integrity, AOP or the 10-year storm event; have a geomorphic assessment or feasibility study completed; or are identified within a watershed-based plan as a priority action item are identified for potential removal. Partners: New Hampshire River Restoration Task Force, NHDES Geological Survey, NHDES Dam Bureau, NHDES Water Quality Section, dam owners, NHFG, watershed organizations and municipalities. | Measure H-3.1 By 2029, at least one dam or barrier removal project receiving partial funding from the NPS Management Program results in restoration of designated uses and an EPA-approved Type I or Type II NPS Success Story that documents a fully or partially restored waterbody respectively. See Milestone PW-3.3. | No data | No data | No data | No data | Yes | Sally Soule | Kevin Lucey | On Schedule | Efforts are underway to conduct removal of the Gonic Dams in Rochester, NH
Objective H-4 Develop 'how to' modules for incorporating multi-benefit stream crossings into watershed-based plans, Hazard Mitigation Plans, Road Safety Plans, Capital Improvement Plans and similar planning documents or initiatives that balance resilience, public safety and watershed integrity. | Milestone H-4.1 A series of instructive manuals is developed to guide stream crossing practitioners and project partners that clearly illustrate the financial, public safety, environmental and resilience multi-benefits when stream crossings are properly sized and installed. Partners: NHDES Coastal Program, NHDES Water Quality Section, NHFG, NHDES Geological Survey, watershed organizations, TNC, municipalities, regional planning commissions and NHDOT. | Measure H-4.1 By 2029, at least one watershed-based plan, hazard mitigation plan, road safety plan, capital improvement plan or similar planning documents or initiatives include the multi-benefit stream crossing approach module criteria as recommendations or requirements. | No data | No data | No data | No data | Yes | Steve Landry | Polly Perkins |  | Awaiting input from Polly
| Milestone H-4.2 Stream crossing prioritization planning training modules are developed that present the information contained in the instructive manuals for prioritizing stream crossings to achieve multi-benefits. Partners: NHDES Coastal Program, NHDES Water Quality Section, NHFG, NHDES Geological Survey, watershed organizations, TNC, municipalities, regional planning commissions and NHDOT. | Measure H-4.2 By 2028, one in-person and one virtual training module have been developed and facilitated for interested stream crossing prioritization planning and implementation stakeholders and practitioners. | No data | No data | No data | Yes | No data | Steve Landry | Polly Perkins |  | Awating input from Polly

## Subsurface
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective S-1 Reduce nitrogen and phosphorus pollution and bacterial contamination from septic systems through system maintenance, system replacement, alternative technologies and development of community systems. | Milestone S-1.1 Alternative technologies that reduce nitrogen export to Great Bay are evaluated and demonstrated. Partners: Conservation districts, Granite State Onsite Wastewater Association (GSOWA), watershed associations, Conservation Law Foundation (CLF), PREP and MAAM. | Measure S-1.1a Candidate sites are identified for the installation of denitrifying systems in the Great Bay watershed. | Yes | Yes | Yes | No data | No data | Sally Soule |  | No Work Scheduled
|  | Measure S-1.1b One denitrifying system in the Great Bay watershed is implemented and the performance is evaluated. | No data | No data | No data | Yes | Yes | Sally Soule |  | No Work Scheduled
| Milestone S-1.2 The capacity is developed to implement a community septic system in a watershed that has an approved watershed-based plan. Partners: GSOWA, NHMA, CWSRF, municipalities, watershed associations and regional planning commissions. | Measure S-1.2 A candidate community septic system site is identified. | No data | No data | No data | Yes | Yes | Sally Soule |  | No Work Scheduled
| Milestone S-1.3 Opportunities for septic system replacement and development of community systems are provided. Partners: NHDES, GSOWA, NHMA, CWSRF, New Hampshire Health Officers Association, New Hampshire Building Officials Association, PREP, New Hampshire Housing Authority and USDA Rural Development | Measure S-1.3a CWSRF loans and other funding sources are available for septic system replacements or community systems. | Yes | Yes | Yes | Yes | Yes | Sally Soule |  | No Work Scheduled
|  | Measure S-1.3b Nonpoint Source Management Program staff coordinate with CWSRF staff on opportunities for increasing access to CWSRF funding for septic system replacement projects. | No data | Yes | Yes | Yes | No data | Sally Soule |  | No Work Scheduled
| Milestone S-1.4 Septic system evaluation and priority ranking are conducted for the replacement of older, malfunctioning septic systems in high-quality waters, watersheds with bacteria and nutrient impairments, or areas at risk from inundation due to sea level rise; implement septic system replacement programs for high-priority systems. Partners: Watershed associations, municipalities, RPCs, conservation districts and NHCP. | Measure S-1.4a A list of septic systems is developed for replacement prioritization in high-quality and/or impaired waters or for coastal waters identified as being at future risk from inundation due to sea level rise. | Yes | Yes | No data | No data | No data | Sally Soule |  | No Work Scheduled
|  | Measure S-1.4b At least two priority systems are replaced, and pollutant load reductions are quantified. | No data | No data | Yes | Yes | Yes | Sally Soule |  | No Work Scheduled
Objective S-2 Research approaches and policies for improved septic system management. | Milestone S-2.1 State legislative and municipal activity relative to septic system regulations are tracked and incorporate new legislation and regulations, if enacted, into NPS programs and projects. Partner: NHDES. | Measure S-2.1 NPS Management Program staff track and promote state and municipal activities relative to septic systems. Any changes are incorporated into NPS programs and projects as relevant. | Yes | Yes | Yes | Yes | Yes | Sally Soule |  | Completed for FY | Staff regularly track legislative and municipal activity relative to septic systems. Updates on regulatory activity are shared with project partners to inform project efforts.
| Milestone S-2.2 Output and recommendations are incorporated from the PREP septic system expert panel process, NHSSSC and the state's cyanobacteria plan into septic system projects and programs as appropriate. Partners: PREP, NHDES, NHCP, MAAM, NHSSSC, UNHSC and RPCs. | Measure S-2.2 The outcomes from PREP expert panel, NHSSC and New Hampshire's cyanobacteria plan are reviewed by NPS Management Program staff to identify opportunities and incorporate recommendations into septic system projects and program work. | Yes | Yes | Yes | No data | No data | Sally Soule |  | No Work Scheduled
| Milestone S-2.3 Through collaboration with coastal partners, opportunities are identified to prioritize and address coastal septic systems at- risk due to inundation from sea level rise. Partners: NHCP, New Hampshire Coastal Adaptation Workgroup (NHCAW), PREP, RPCs and municipalities. | Measure S-2.3 NPS Management Program staff coordinates with partners to identify opportunities for collaboration on projects to better understand and address future risks to septic systems. | No data | No data | Yes | Yes | Yes | Steve Landry | Jennifer Gilbert, Kirsten Howard, and Andrew Koff | No Work Scheduled | Portsmouth Vulnerability Study ongoing with recent meeting on 09172025. NPS staff will investigate returns on attending monthly meetings to receive updates and links to septic system vulnerability that may align with the groundwater monitoring data with asset management strategies being discussed.

## Transportation
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective T-1 New Hampshire commercial salt applicators are trained and Green SnowPro certified in winter snow and ice management best practices. | Milestone T-1.1 Voluntary commercial salt applicators are trained in winter snow and ice management best practices each year. Partners: NHDES NPS Management Program, UNH T2, SASC and SIMA. | Measure T-1.1 At least 1,250 voluntary commercial salt applicators complete Green SnowPro approved certification training within five years. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule
| Milestone T-1.2 Voluntary commercial salt applicators demonstrate proficiency in and the use of salt reduction practices through Green SnowPro approved training and receive Green SnowPro certification from NHDES. Partners: NHDES NPS Management Program, UNH T2, SASC and SIMA. | Measure T-1.2 At least 550 voluntary commercial salt applicators receive Green SnowPro certification each year. | Yes | Yes | Yes | Yes | Yes | Aubrey Voelker |  | Completed for FY | 712 Green SnowPro certificates issued for the 2024/2025 winter season. Over 300 certificates already issued for the 2025/2026 winter season
Objective T-2 NHDES has an increased understanding of the amount of winter salt applied in New Hampshire. | Milestone T-2.1 The number of voluntary commercial and municipal salt applicators submitting annual salt use reports increases. Partners: NHDES NPS Management Program and salt applicators. | Measure T-2.1a Reporting and re-certification reminders are sent annually to Green SnowPro certified salt applicators. | Yes | Yes | Yes | Yes | Yes | Aubrey Voelker |  | Completed for FY
|  | Measure T-2.1b 100% of voluntary commercial and municipal salt applicators seeking re-certification submit an annual salt use report to NHDES. | Yes | Yes | Yes | Yes | Yes | Aubrey Voelker |  | Completed for FY
| Milestone T-2.2 Analyze salt use/salt loading data received from NHDOT, Town of Merrimack, commercial salt applicators, Merrimack Village District (MVD) and homeowners within the Naticook Brook watershed and generate sector load allocation, adjusted for weather severity. Partners: NHDES, NHDOT, MVD, Town of Merrimack and other watershed salt applicators. | Measure T-2.2 The NaCl-specific watershed-based plan for the Naticook Brook watershed is published and includes winter salt sector load allocations. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule
Objective T-3 Identify and prioritize watersheds with chloride impairments for salt reduction initiatives. | Milestone T-3 Engage with communities and commercial contractors in at least one priority watershed for Green SnowPro certification and implementation of salt reduction strategies. Partners: NHDES NPS Management Program and Green SnowPro Commercial Contractors. | Measure T-3 Municipal and commercial salt applicators are certified as Green SnowPro within a priority watershed and engage with NHDOT and residents (where applicable) to adopt salt reduction best practices. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule | Began looking at who owns and manages properties surrounding Mink, Dartmouth, and Trout Brooks to later begin outreach on salt reduation practices and Green SnowPro certification.
Objective T-4 Educate MS4 communities and enable them to implement salt reduction practices. | Milestone T-4* Work with MS4 communities and assist with addressing chloride impairments, salt reduction and snow and ice management best practices. Partners: NHDES NPS Management Program and New Hampshire MS4 communities. | Measure T-4 Guidance and templates are provided to the New Hampshire MS4 communities through the New Hampshire stormwater coalitions. | Yes | Yes | Yes | Yes | Yes | Deb Loiselle | Tom Swenson & Aubrey Voelker | Completed for FY | Assist with reminding and collecting Annual Salt Usage Reports to meet the 2017 NH MS4 permit requirements for chloride impaired and TMDL surface waters. All 16 required permittees submitted their reports. In addition, 3 permittees voluntarily submitted their reports. Reminders about winter maintenance practices are routinely done at the monthly NHLMV and SSC meetings in addition to pertinent resources and trainings through NHDES and UNHT2. The 2025 Annual Salt Symposium was held on 9/10/25 and for the 3rd year had a dedicated municipal track. There were 10 NH MS4 permittees represented.
Objective T-5 New Hampshire municipal salt applicators are trained and Green SnowPro certified in winter maintenance best practices. | Milestone T-5.1 Voluntary municipal salt applicators are trained in winter maintenance best practices each year. Partners: NHDES NPS Management Program, UNH T2, SASC and SIMA. | Measure T-5.1 At least 120 voluntary municipal salt applicators completed Green SnowPro approved certification training within five years. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule
| Milestone T-5.2 Voluntary municipal salt applicators demonstrate proficiency in and use of salt reduction practices through Green SnowPro approved training and municipalities receive Green SnowPro certification from NHDES. Partners: NHDES NPS Management Program, UNH T2, SASC and SIMA. | Measure T-5.2 At least 30 municipalities are certified by the Municipal Winter Maintenance Certification (Green SnowPro) Program by 2029. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule | 2 municipalities are currently Green SnowPro certified (Portsmouth and Hooksett). More municipalities have expressed interest in seeking certificaiton in future years.
Objective T-6 Update the New Hampshire Voluntary Green SnowPro certification curriculum and best practices manual. | Milestone T-6 Salt applicators certified as Green SnowPro receive state of the art salt reduction practice training, proficiency exams, an industry standard best practices manual and up-to-date training materials and associated reference materials. Partners: NHDES NPS Management Program, SIMA, Harrier, LLC, UNH T2 and SASC. | Measure T-6 Updated and industry standard winter salt reduction best practices manual and training materials are available for new and existing Green SnowPro certified salt applicators. | No data | No data | No data | No data | Yes | Aubrey Voelker |  | On Schedule | In the final stages of completing the updated BMP manual. Final reviews from stakeholders and ADA compliance review will be underway soon.

## LawnsandTurf
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective L-1 Fertilizer from lawns and turfgrass management practices does not degrade water quality. | Milestone L-1.1 NPS partners and stakeholders have access to and an understanding of current soil, turf, water quality and social sciences in order to reduce water quality impacts from lawns and turfgrass management practices related to fertilizer application. Partners: UNH Extension, New Hampshire Sea Grant, NHDES Coastal Program, Conservation Districts, New Hampshire Department of Agriculture, Markets and Foods, NEIWPCC, Master Gardeners, garden clubs, 319 Grantees, Natural Resource Stewards, professional landscapers and turf managers. | Measure L-1.1a The current science, research, outreach resources and BMPs related to fertilizer impacts to water quality from lawns and turfgrass management is tracked and documented as a dynamic list of links that will be reviewed and updated at least every five years. Information is obtained from Department of Agriculture, UNH Extension and Sea Grant and NEIWPCC. | No data | No data | No data | No data | Yes | Tom Swenson |  | On Schedule
|  | Measure L-1.1b Current water quality and landscaping/turf management science research, outreach messaging and events are posted to NHDES social media venues (blogs and Facebook) quarterly. | Yes | Yes | Yes | Yes | Yes | Tom Swenson |  | Behind Schedule | No related outreach, events, or materials were shared on NHDES social media accounts during 2025. I will work with NHDES communications staff to get related information posted in 2026.
|  | Measure L-1.1c Information on water quality impacts from lawns and turfgrass fertilizer, management practices and BMPs to protect water resources is provided to partners and other organizations conducting outreach on related topics. | Yes | Yes | Yes | Yes | Yes | Tom Swenson |  | Completed for FY | Presented new and old lawn and turf management outreach resources to the New Hampshire Lower Merrimack Valley Stormwater Coalition and Seacoast Stormwater Coalition during the monthly May meetings. The outreach covered topics such as fertilizer use and water recommendations.
| Milestone L-1.2 New Hampshire residents are aware of BMPs to reduce water quality impacts from lawn care activities including fertilizer use. Partners: UNH Extension and New Hampshire Sea Grant. | Measure L-1.2a Existing homeowner outreach program components focused on fertilizer use are regularly evaluated. | Yes | Yes | Yes | Yes | Yes | Tom Swenson |  | Completed for FY | The existing fertilizer outreach materials were evaluated and no updates were needed this year.
|  | Measure L-1.2b New outreach messages and methods identified in Measure L-1.2a evaluations are created, updated and implemented. | Yes | Yes | Yes | Yes | Yes | Tom Swenson |  | On Schedule | No new fertilizer outreach messages or materials were created this year since it determined that no updates were needed.
| Milestone L-1.3 Landscapers and lawn care professionals are aware of and incorporate BMPs to reduce water quality impacts from fertilizer applications. Partners: New Hampshire Landscape Association, UNH Extension and New Hampshire Sea Grant | Measure L-1.3a Two Landscaping for Water Quality Workshops are hosted by 2029. | No data | Yes | No data | Yes | No data | Tom Swenson |  | No Work Scheduled | No work for 2025
|  | Measure L-1.3b Participants of the Landscaping for Water Quality Workshop and list are tracked on the UNH Extension website. | No data | Yes | No data | Yes | No data | Tom Swenson |  | No Work Scheduled | No work for 2025
| Milestone L-1.4 Garden centers, nurseries and town halls promote BMPs to reduce water quality impacts from fertilizer use. Partners: UNH Cooperative Extension, New Hampshire Sea Grant, New Hampshire Plant Growers Association, garden centers, plant nurseries, New Hampshire MS4 communities and watershed groups. | Measure L-1.4 Outreach materials on best fertilizer practices are created and offered to at least two garden centers, nurseries and town halls. | No data | No data | No data | Yes | No data | Tom Swenson |  | On Schedule
| Milestone L-1.5 Municipal field managers are aware of and use BMPs to reduce water quality impacts from turfgrass management. Partners: NHDES Coastal Program, New Hampshire Municipal Association, New Hampshire stormwater coalitions, UNH Extension and New Hampshire Sea Grant. | Measure L-1.5* Guidance and tools regarding BMPs for municipal turf management and water quality are promoted to local decision makers, New Hampshire MS4 permit responsible staff, municipal field managers and other interested parties. | Yes | No data | Yes | No data | Yes | Tom Swenson |  | Completed for FY | Presented new and old lawn and turf management outreach resources to the New Hampshire Lower Merrimack Valley Stormwater Coalition and Seacoast Stormwater Coalition during the monthly May meetings. The outreach covered topics such as fertilizer use and water recommendations.

## Agriculture
Objective | Milestone | Measure of Success | 2025 | 2026 | 2027 | 2028 | 2029 | WAS Lead | Key Contacts | 2025 Status | 2025 Comments
Objective A-1 Foster good agricultural management through education, training and certification programs. | Milestone A-1.1 Work to recruit new technical service providers for nutrient management, grazing practices and soil health planning. Partners: Conservation districts, NRCS, NHDAMF and UNH Extension. | Measure A-1.1 Outreach to attract new agricultural technical service providers is conducted and three new service providers are recruited to enter NRCS' Technical Service Provider Program. | No data | No data | No data | Yes | No data | Steve Landry |  | No Work Scheduled
| Milestone A-1.2 Agricultural BMPs and BMWPs are promoted through training workshops on BMPs for Agriculture, the 2019 Wetland Rules and 2019 BMWPs for Agriculture. Partners: NHDAMF, NRCS and UNH Extension. | Measure A-1.2 Two training workshops are held by 2029. | No data | Yes | No data | Yes | No data | Steve Landry |  | No Work Scheduled
| Milestone A-1.3 Conservation and improved soil health are promoted through the continued support of education and technical assistance to agriculture operations, including small scale farmers. Partners: New Hampshire Association of Conservation Districts (NHACD), NHDAMF, NRCS and UNH Extension. | Measure A-1.3 Outreach and technical assistance and partner engagement is provided through four events each year. | Yes | Yes | Yes | Yes | Yes | Steve Landry |  | Behind Schedule | Will contact our partners and secue end of year updates.
Objective A-2 Implementation of agricultural best management practices. | Milestone A-2.1 Buffers and streambank stabilization practices on agricultural lands, including working buffers are promoted. Partners: Conservation districts, NRCS and UNH Extension. | Measure A-2.1 Riparian buffers are installed on 25 properties, encompassing 25 acres by 2029. | No data | No data | No data | No data | Yes | Steve Landry |  | No Work Scheduled
| Milestone A-2.2 Increase the number of farms with nutrient management plans. Partners: Conservation Districts, NHDAMF and UNH Extension. | Measure A-2.2a Nutrient management plans are developed for 15 new farms by 2029. | No data | No data | No data | No data | Yes | Steve Landry |  | No Work Scheduled
|  | Measure A-2.2b Agricultural BMPs are promoted through outreach and education to landowners on tax exempt status for certain water pollution control facilities under RSA 72:12-a. At least two outreach elements are created. | No data | No data | Yes | No data | Yes | Steve Landry |  | No Work Scheduled
| Milestone A-2.3 IPM practices are encouraged. Partners: NHACD, NHDAMF, NRCS and UNH Extension. | Measure A-2.3 Continued work with the IPM workgroup. Outreach to farms is provided and 10 new IPM plans for private landowners are developed each year. | Yes | Yes | Yes | Yes | Yes | Steve Landry |  | Behind Schedule | Will contact our partners and secue end of year updates.
Objective A-3 Support conservation easements for Agriculture. | Milestone A-3.1 Farms or farmland parcels under Agricultural easements are promoted. Partners: Land and Community Heritage Investment Program (LCHIP), NHDAMF, NH Farm Bureau and NRCS. | Measure A-3.1 Twenty-five new Agricultural Land Easements (ALE) and Wetland Reserve Easements (WRE), encompassing 4,000 acres are obtained by 2029. | No data | No data | No data | No data | Yes | Steve Landry |  | No Work Scheduled
Objective A-4 Funding opportunities are maximized through partnerships with USDA and local stakeholders to make the best use of available resources to address NPS pollution. | Milestone A-4.1 Attract funding to leverage Long Island Sound Futures Fund to protect and improve water quality in New Hampshire as it relates to agricultural activities. Partners: State Technical Committee Members. | Measure A-4.1 Presentations are given at one State Tech Committee per year on topics such as NWQI or Conservation Reserve Program (CRP). | Yes | Yes | Yes | Yes | Yes | Steve Landry |  | Completed for FY | One presentation delivered and LISFF resources distributed to partners.
| Milestone A-4.2 Work with NRCS to develop an approved watershed assessment/management plan and provide monitoring support to measure effectiveness of BMPs and conservation efforts within one NWQI priority watershed. Partners: NHDES NPS Management Program, NRCS, watershed coalitions, conservancies and commissions. | Measure A-4.2a Annual water quality monitoring is conducted to track trends in water quality in the Clark and Oliverian Brook watersheds to measure the effectiveness of agricultural BMPs on working land. | Yes | Yes | Yes | Yes | Yes | Steve Landry | EPA and NRCS | Completed for FY | WAS on schedule until government shutdown eliminated October sampling.
|  | Measure A-4.2b Through partner engagement, outreach and NRCS programs, the Kearsarge Brook alternative plan for the Saco is developed. | No data | No data | No data | No data | Yes | Steve Landry |  | No Work Scheduled